## Product End Point Backlog
ENDPOINT ID | ENDPOINT TITLE | ENDPOINT STORY | API METHOD | API ENDPOINT | ACTOR | FUNCTION FLOW | AUTHORS | ASSIGNEE | STATUS | REMARK (IF ANY)
Customer Login Microservice
EP01 | Login to customer's account | A customer should be able to Login into his account through EmailId and Password. | POST | /loginbymail | Customer | 1.Open URL in postman software to check endpoint. 2.Enter api endpoint. 3.Enter emailid and password in JSON format. 4.Click send button. 5.Customer will be logged into his aacount. | Divyesh | Divyesh | Completed
|  | A customer should be able to Login into his account through EmailId and Password. | POST | /loginbyphonenumber | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Enter mobile number and password in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Divyesh | Divyesh | Completed
EP02 | SignUp to Infy-Aerspace | A customer should be able to signup to the portal by using his details. | POST | /register | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Enter mobile number and password in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Divyesh | Divyesh | Completed
EP03 | Viewing a customer's profile | A customer should be able to view his profile through his customerid generated st time of sign up. | GET | /view/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Divyesh | Divyesh | Completed
Manufacture Air Bus Microservice
EP04 | View all air bus models | An authenticated customer can view all the different models present in the database. | GET | /airbusmodels/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Shravya | Shravya | Completed
EP05 | View air bus based on manufacture model number | An authenticated customer can view model present in the database. | GET | /modelid/{customerid}/{manufacture_model_no} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Shravya | Shravya | Completed
EP06 | View air bus based on model name | An authenticated customer can view model present in the database. | GET | /modelname/{customerid}/{model_name} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Shravya | Shravya | Completed
EP07 | An order | 1. A customer`s order based on the quotation model number he has. 2. Quotation model number should be same to manufacturing model number present in the database. 3. Display appropriate message after customer has placed the order | POST | /order/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Enter quotation model number and other details in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Shravya | Shravya | Completed
EP08 | Deleting an order | An order can be discarded by the customer using the order Id, as per his convenince | DELETE | /delete/{customerid}/{order_id} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint with delete service 3. Enter orderId in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Shravya | Shravya | Completed
Manufacture Jets Microservice
EP09 | View all jet models | An authenticated customer can view all the different models present in the database. | GET | /jetmodels/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Raghul | Raghul | Completed
EP10 | View jet based on manufacture model number | An authenticated customer can view model present in the database. | GET | /modelid/{customerid}/{manufacture_model_no} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Raghul | Raghul | Completed
EP11 | View jet based on model name | An authenticated customer can view model present in the database. | GET | /modelname/{customerid}/{model_name} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Raghul | Raghul | Completed
EP12 | An order | 1. A customer`s order based on the quotation model number he has. 2. Quotation model number should be same to manufacturing model number present in the database. 3. Display appropriate message after customer has placed the order | POST | /order/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Enter quotation model number and other details in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Raghul | Raghul | Completed
EP13 | Deleting an order | An order can be discarded by the customer using the order Id, as per his convenince | DELETE | /delete/{customerid}/{order_id} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint with delete service 3. Enter orderId in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Raghul | Raghul | Completed
Traffic Control System Microservice
EP14 | View all control models | An authenticated customer can view all the different models present in the database. | GET | /controlmodels/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Thayamma | Thayamma | Completed
EP15 | View control based on manufacture model number | An authenticated customer can view model present in the database. | GET | /modelid/{customerid}/{manufacture_model_no} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Thayamma | Thayamma | Completed
EP16 | View control based on model name | An authenticated customer can view model present in the database. | GET | /modelname/{customerid}/{model_name} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Click send button. 4. Appropriate message will be displayed with required data to customer. | Thayamma | Thayamma | Completed
EP17 | An order | 1. A customer`s order based on the quotation model number he has. 2. Quotation model number should be same to manufacturing model number present in the database. 3. Display appropriate message after customer has placed the order | POST | /order/{customerid} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint. 3. Enter quotation model number and other details in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Thayamma | Thayamma | Completed
EP18 | Deleting an order | An order can be discarded by the customer using the order Id, as per his convenince | DELETE | /delete/{customerid}/{order_id} | Customer | 1. Open URL in postman software to check endpoint. 2. Enter api endpoint with delete service 3. Enter orderId in JSON format. 4. Click send button. 5. Appropriate message will be displayed. | Thayamma | Thayamma | Completed

## Day-wise Backlog
DAY | ENDPOINT ID | TASK ID | TASK DESCRIPTION | TASK START DATE | TASK COMPLETION DATE | TEAM MEMBER | ACTIVITY | STATUS
1 | N/A | T01 | Stand-up meeting | 2020-08-18 | 2020-08-22 | Divyesh, Raghul, Shravya, Thayamma | Meeting | Completed
|  | T02 | Studying specification document | 2020-08-18 | 2020-08-18 | Divyesh, Raghul, Shravya, Thayamma | Reading | Completed
|  | T03 | Creating test cases for specification document | 2020-08-18 | 2020-08-19 | Divyesh, Raghul, Shravya, Thayamma | Writing | Completed
|  | T19 | Table Scripts formation with precise schema | 2020-08-18 | 2020-08-19 | Divyesh, Raghul, Shravya, Thayamma | Code Development | Completed
|  | T05 | Sonar Lint updation on ecilipse | 2020-08-18 | 2020-08-19 | Divyesh, Raghul, Shravya, Thayamma | Tool Enhancement | Completed
2 | EP01 | T06 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Divyesh | Code Development | Completed
|  | T07 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T08 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
| EP04 | T09 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Shravya | Code Development | Completed
|  | T10 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T11 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
| EP05 | T12 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Shravya | Code Development | Completed
|  | T13 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T14 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
| EP09 | T15 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Raghul | Code Development | Completed
|  | T16 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T17 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
| EP10 | T18 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Raghul | Code Development | Completed
|  | T19 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T20 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
| EP14 | T21 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Thayamma | Code Development | Completed
|  | T22 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T23 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
| EP15 | T24 | Code Development And Table Script Execution | 2020-08-19 | 2020-08-20 | Thayamma | Code Development | Completed
|  | T25 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-20 |  | Deployment | Completed
|  | T26 | Testing API Endpoint in Postman | 2020-08-20 | 2020-08-21 |  | Testing | Completed
3 | EP02 | T27 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Divyesh | Code Development | Completed
|  | T28 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T29 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP03 | T30 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Divyesh | Code Development | Completed
|  | T31 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T32 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP06 | T33 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Shravya | Code Development | Completed
|  | T34 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T35 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP07 | T36 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Shravya | Code Development | Completed
|  | T37 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T38 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP08 | T39 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Shravya | Code Development | Completed
|  | T40 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T41 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP11 | T42 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Raghul | Code Development | Completed
|  | T43 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T44 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP12 | T45 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Raghul | Code Development | Completed
|  | T46 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T47 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP13 | T48 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Raghul | Code Development | Completed
|  | T49 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T50 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP16 | T51 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Thayamma | Code Development | Completed
|  | T52 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T53 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP17 | T54 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Thayamma | Code Development | Completed
|  | T55 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T56 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP18 | T57 | Code Development And Table Script Execution | 2020-08-20 | 2020-08-20 | Thayamma | Code Development | Completed
|  | T58 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 |  | Deployment | Completed
|  | T59 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
4 | EP6 | T34 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 | Shravya | Deployment | Completed
|  | T35 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP8 | T40 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 | Shravya | Deployment | Completed
|  | T41 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP12 | T46 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 | Raghul | Deployment | Completed
|  | T47 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP13 | T49 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 | Raghul | Deployment | Completed
|  | T50 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP18 | T58 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 | Thayamma | Deployment | Completed
|  | T59 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| EP17 | T55 | Executing Microservice and Resolving Errors | 2020-08-20 | 2020-08-21 | Thayamma | Deployment | Completed
|  | T56 | Testing API Endpoint in Postman | 2020-08-21 | 2020-08-21 |  | Testing | Completed
| N/A |  | Sonar Upload | 2020-08-21 | 2020-08-22 | All | Deployment | In Progress

## Retrospection
Start date | End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
2020-08-18 | 2020-08-18 | Divyesh,Shravya | T01,T05 | T05 | T01,T05 | Sonar lint updated on eclipse
2020-08-18 | 2020-08-19 | Divyesh,Raghul,Shravya,Thayamma | T01,T02,T03,T04 | T02,T03 | T01,T04 | Studied specification document and created test cases
2020-08-19 | 2020-08-20 | Divyesh,Raghul | T06,T07,T08,T12,T13,T14 | T06,T12 | T07,T08,T13,T14 | Code Development
2020-08-19 | 2020-08-19 | Shravya,Thayamma | T01,T04 | T04 | T01 | Table Scripts discussion
2020-08-19 | 2020-08-20 | Shravya,Raghul | T9,T10,T11 | T9,T10 | T11 | Code Development
2020-08-20 | 2020-08-21 | Thayamma,Raghul | T15,T16,T17 | T15 | T16,T17 | Code Development
2020-08-20 | 2020-08-21 | Divyesh,Raghul,Shravya,Thayamma | T18 to T59 | T18 to T59 | N/A | Code Development
2020-08-21 | 2020-08-22 | Divyesh,Raghul,Shravya,Thayamma | T18 to T59 | N/A | T18 to T59 | Endpoints Check

## Standup meeting
DAY | DATE | TIME | DURATION | END POINT CASES ID | ASSIGNED TO | POINTS DISCUSSED | SNAG LIST | MILESTONES | ACTION TAKEN
1 | 2020-08-18 | 10:30 | 45 min | N/A |  | 1. Reading out the use case document. 2. Allotment of microservices. 3. Evaluating an overview of project. | 1.Understanding the specification document. 2.Table Script formation. 3.Swagger Implementation. 4.Comprehensive overview. | 1. Test case writing. 2. Table scripts. | 1. Writing test cases for Alloted microservice 2. Evaluating Schema for table scripts of individual microservices
|  | 17:00 | 90 min |  |  | 1. Brainstorming on database schema 2. Swagger api discussion eliminating impediments 3. Overview of in progress table scripts | Database Schema. |  | 1. Worked on in progress table scripts 2. Swagger api demo discussion and exchanging views
2 | 2020-08-19 | 9:45 | 60 min | N/A |  | 1. Attributes in tables for microservices 2. Test cases discussion | 1. Flow of the test cases. 2. Schema correction. | 1. Final table scripts. 2.Test case understanding. | 1. Resolved the test case anomolies 2. Confusion for attributes was clarified
|  | 12:30 | 15 min | N/A | Divyesh, Raghul, Shravya, Thayamma | Table attributes discussion | Flow of data concerning attributes to be taken in the relation | Table scripts | table attributes was finalize.
|  | 1:45 | 30 min | EP01-EP18 | Divyesh, Raghul, Shravya, Thayamma | Flow of data present the test case | Data details | Completing task | Resolving the doubts regarding test case
3 | 2020-08-20 | 12:30 | 2 hrs |  | Divyesh, Raghul, Shravya, Thayamma | Code development and execution | Endpoint working status | To make code work | Resolving the errors and develop accordingly
4 | 2020-08-21 | 10:30 | 3hrs |  | Divyesh, Raghul, Shravya, Thayamma | Code development and execution | Endpoint working status | To make code work | Resolving the errors and develop accordingly
5 | 2020-08-22 | 10:30 | 30 min |  | Divyesh, Raghul, Shravya, Thayamma | Final review | N/A | Microservice to work properly | Resolve all upcoming issues